## DATA
# | Fiscal Year | SEMESTER | PLANNER BUCKET | TASK | ASSIGNMENT TITLE | AUDIENCE | START | END | PROGRESS
1 | 2026 |  | Theme Meal | Potato Bowl -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
2 | 2026 |  | Theme Meal | Homecoming Celebration -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
3 | 2026 |  | Theme Meal | Chili Challenge | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
4 | 2026 |  | Theme Meal | Halloween Spook-tacular Hocus Pocus Themed -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
5 | 2026 |  | Theme Meal | Alaska Seafood Sustainable Dinner | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
6 | 2026 |  | Theme Meal | Winter Wonderland -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
7 | 2026 |  | Theme Meal | Wing Challenge (Wilkerson Commons) | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
8 | 2026 |  | Theme Meal | Mardi Gras Dinner -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
9 | 2026 |  | Theme Meal | Student Chopped Competition | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
10 | 2026 |  | Theme Meal | Time-Out Week Menu | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
11 | 2026 |  | Theme Meal | Celebrate Earth Day | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
12 | 2026 |  | Theme Meal | Star Wars Theme Dinner | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
13 | 2026 |  | Camps and Conferences | Summer Camp/Conference Staff Selection Begins | Associate Director of Residence Life |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
14 | 2026 |  | Theme Meal | Black History Month | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
15 | 2026 |  | Theme Meal | Latin American | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
16 | 2026 |  | Theme Meal | Vendor Showcase | Dining/Catering |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
17 | 2026 |  | Camps and Conferences | Summer Conference Registration Opens | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
18 | 2026 |  | Camps and Conferences | Summer Conference Sponsor Meetings Begin | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
19 | 2026 |  | Camps and Conferences | Summer Guest Housing Opens (Swanson) | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
20 | 2026 |  | Billing and Financial | Fall Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
21 | 2026 |  | Billing and Financial | Apartment August Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
22 | 2026 |  | Billing and Financial | Apartment September Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
23 | 2026 |  | Billing and Financial | Apartment October Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
24 | 2026 |  | Billing and Financial | Apartment November Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
25 | 2026 |  | Billing and Financial | Apartment December Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
26 | 2026 |  | Billing and Financial | Spring Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
27 | 2026 |  | Billing and Financial | Apartment January Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
28 | 2026 |  | Billing and Financial | Apartment February Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
29 | 2026 |  | Billing and Financial | Apartment March Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
30 | 2026 |  | Billing and Financial | Apartment April Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
31 | 2026 |  | Billing and Financial | Apartment May Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
32 | 2026 |  | Billing and Financial | Summer Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
33 | 2026 |  | Billing and Financial | Apartment June Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
34 | 2026 |  | Billing and Financial | Apartment July Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
35 | 2026 |  | Health and Life Safety | Residence Hall Fall Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
36 | 2026 |  | Health and Life Safety | Fall Health & Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
37 | 2026 |  | Health and Life Safety | Fall End of Semester Closing Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
38 | 2026 |  | Health and Life Safety | Residence Hall Spring Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
39 | 2026 |  | Health and Life Safety | Spring Health & Safety Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
40 | 2026 |  | Health and Life Safety | Spring Closing Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
41 | 2026 |  | Health and Life Safety | Summer Health & Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
42 | 2026 |  | Health and Life Safety | Residence Hall Summer Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
43 | 2026 |  | Planning | Update Ops Calendar |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
44 | 2026 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
45 | 2026 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
46 | 2026 |  | Recognition | RA Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
47 | 2026 |  | Recognition | Student Staff Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
48 | 2026 |  | Recognition | ARH Banquet | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
49 | 2026 |  | Recognition | Student Staff Banquet |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
50 | 2026 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
51 | 2026 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
52 | 2026 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
53 | 2026 |  | Student Leadership | ARH Executive Board Orientation | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
54 | 2026 |  | Student Leadership | ARH Move-Crew Orientation | Asst Director, Residential Experiences |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
55 | 2026 |  | Student Leadership | Hall Government Recruitment & Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
56 | 2026 |  | Student Leadership | ARH First Official Meeting | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
57 | 2026 |  | Student Leadership | Derrick Hanson Scholarship Process | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
58 | 2026 |  | Student Leadership | NRHH Leadership Scholarships Applications Period | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
59 | 2026 |  | Student Leadership | ARH Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
60 | 2025 |  | Academic | Current Student, 3 month payment plan opens |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
61 | 2025 |  | Academic | Fall Last Day to change to/from audit grading for Full-Term course |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
62 | 2025 |  | Academic | Satisfactory Academic Progress petitions due |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
63 | 2025 |  | Academic | Report on unsatisfactory progress (deficiencies)due from faculty to starfish |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
64 | 2025 |  | Academic | Spring UND bookstore charing begins |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
65 | 2025 |  | Academic | Spring Satisfactory Academic Progress petitions due |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
66 | 2025 |  | Academic | Summer Last Day to add course or drop without record |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
67 | 2025 |  | Academic | Summer Last Day to drop with record |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
68 | 2024 |  | Theme Meal | Black History Month | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
69 | 2024 |  | Theme Meal | Latin American | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
70 | 2024 |  | Theme Meal | Vendor Showcase | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
71 | 2024 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
72 | 2024 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
73 | 2024 |  | Recognition | RA Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
74 | 2024 |  | Recognition | Student Staff Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
75 | 2024 |  | Recognition | ARH Banquet | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
76 | 2024 |  | Recognition | Student Staff Banquet |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
77 | 2024 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
78 | 2024 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
79 | 2024 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
80 | 2024 |  | Student Leadership | ARH Executive Board Orientation | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
81 | 2024 |  | Student Leadership | ARH Move-Crew Orientation | Asst Director, Residential Experiences |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
82 | 2024 |  | Student Leadership | Hall Government Recruitment & Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
83 | 2024 |  | Student Leadership | ARH First Official Meeting | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
84 | 2024 |  | Student Leadership | Derrick Hanson Scholarship Process | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
85 | 2024 |  | Student Leadership | NRHH Leadership Scholarships Applications Period | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
86 | 2024 |  | Student Leadership | ARH Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
87 | 2024 |  | Academic | Current Student, 3 month payment plan opens |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
88 | 2024 |  | Academic | Fall Last Day to change to/from audit grading for Full-Term course |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
89 | 2024 |  | Academic | Satisfactory Academic Progress petitions due |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
90 | 2024 |  | Academic | Report on unsatisfactory progress (deficiencies)due from faculty to starfish |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
91 | 2024 |  | Academic | Spring UND bookstore charing begins |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
92 | 2024 |  | Academic | Spring Satisfactory Academic Progress petitions due |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
93 | 2024 |  | Academic | Summer Last Day to add course or drop without record |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
94 | 2024 |  | Academic | Summer Last Day to drop with record |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | COMPLETE
95 | 2025 |  | Theme Meal | Potato Bowl -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
96 | 2025 |  | Theme Meal | Homecoming Celebration -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
97 | 2025 |  | Theme Meal | Chili Challenge | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
98 | 2025 |  | Theme Meal | Halloween Spook-tacular Hocus Pocus Themed -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
99 | 2025 |  | Theme Meal | Alaska Seafood Sustainable Dinner | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
100 | 2025 |  | Theme Meal | Winter Wonderland -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
101 | 2025 |  | Theme Meal | Wing Challenge (Wilkerson Commons) | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
102 | 2025 |  | Theme Meal | Mardi Gras Dinner -- Housing Program | Marketing/ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
103 | 2025 |  | Theme Meal | Student Chopped Competition | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
104 | 2025 |  | Theme Meal | Time-Out Week Menu | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
105 | 2025 |  | Theme Meal | Celebrate Earth Day | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
106 | 2025 |  | Theme Meal | Star Wars Theme Dinner | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
107 | 2025 |  | Camps and Conferences | Summer Camp/Conference Staff Selection Begins | Associate Director of Residence Life |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
108 | 2025 |  | Theme Meal | Black History Month | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
109 | 2025 |  | Theme Meal | Latin American | Dining |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
110 | 2025 |  | Theme Meal | Vendor Showcase | Dining/Catering |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
111 | 2025 |  | Camps and Conferences | Summer Conference Registration Opens | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
112 | 2025 |  | Camps and Conferences | Summer Conference Sponsor Meetings Begin | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
113 | 2025 |  | Camps and Conferences | Summer Guest Housing Opens (Swanson) | Operations Manager |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
114 | 2025 |  | Billing and Financial | Fall Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
115 | 2025 |  | Billing and Financial | Apartment August Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
116 | 2025 |  | Billing and Financial | Apartment September Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
117 | 2025 |  | Billing and Financial | Apartment October Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
118 | 2025 |  | Billing and Financial | Apartment November Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
119 | 2025 |  | Billing and Financial | Apartment December Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
120 | 2025 |  | Billing and Financial | Spring Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
121 | 2025 |  | Billing and Financial | Apartment January Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
122 | 2025 |  | Billing and Financial | Apartment February Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
123 | 2025 |  | Billing and Financial | Apartment March Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
124 | 2025 |  | Billing and Financial | Apartment April Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
125 | 2025 |  | Billing and Financial | Apartment May Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
126 | 2025 |  | Billing and Financial | Summer Bill Export |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
127 | 2025 |  | Billing and Financial | Apartment June Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
128 | 2025 |  | Billing and Financial | Apartment July Rent Export/Send Rent Reminder |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
129 | 2025 |  | Health and Life Safety | Residence Hall Fall Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
130 | 2025 |  | Health and Life Safety | Fall Health & Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
131 | 2025 |  | Health and Life Safety | Fall End of Semester Closing Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
132 | 2025 |  | Health and Life Safety | Residence Hall Spring Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
133 | 2025 |  | Health and Life Safety | Spring Health & Safety Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
134 | 2025 |  | Health and Life Safety | Spring Closing Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
135 | 2025 |  | Health and Life Safety | Summer Health & Safety Checks |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
136 | 2025 |  | Health and Life Safety | Residence Hall Summer Fire Drills |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
137 | 2025 |  | Planning | Update Ops Calendar |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
138 | 2025 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
139 | 2025 |  | Residential Curriculum |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
140 | 2025 |  | Recognition | RA Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
141 | 2025 |  | Recognition | Student Staff Appreciation Day |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
142 | 2025 |  | Recognition | ARH Banquet | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
143 | 2025 |  | Recognition | Student Staff Banquet |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
144 | 2025 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
145 | 2025 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
146 | 2025 |  | Staff Training and Development |  |  |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
147 | 2025 |  | Student Leadership | ARH Executive Board Orientation | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
148 | 2025 |  | Student Leadership | ARH Move-Crew Orientation | Asst Director, Residential Experiences |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
149 | 2025 |  | Student Leadership | Hall Government Recruitment & Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
150 | 2025 |  | Student Leadership | ARH First Official Meeting | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
151 | 2025 |  | Student Leadership | Derrick Hanson Scholarship Process | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
152 | 2025 |  | Student Leadership | NRHH Leadership Scholarships Applications Period | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
153 | 2025 |  | Student Leadership | ARH Elections | ARH |  | 1900-12-30 (Sunday) | 1900-12-30 (Sunday) | NOT STARTED
154 | 2026 |  | Academic | Current Student, 3 month payment plan opens |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
155 | 2026 |  | Academic | Fall Last Day to change to/from audit grading for Full-Term course |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
156 | 2026 |  | Academic | Satisfactory Academic Progress petitions due |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
157 | 2026 |  | Academic | Report on unsatisfactory progress (deficiencies)due from faculty to starfish |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
158 | 2026 |  | Academic | Spring UND bookstore charing begins |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
159 | 2026 |  | Academic | Spring Satisfactory Academic Progress petitions due |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
160 | 2026 |  | Academic | Summer Last Day to add course or drop without record |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
161 | 2026 |  | Academic | Summer Last Day to drop with record |  |  | 1901-12-30 (Monday) | 1901-12-30 (Monday) | NOT STARTED
162 | 2024 |  | Policy and Contrtact | RH Contract | Asst Director, Operations |  | 2023-08-27 (Sunday) | 2023-08-27 (Sunday) | COMPLETE
163 | 2024 |  | Planning | Create Time Frames | Asst Director, Operations |  | 2023-09-02 (Saturday) | 2023-09-02 (Saturday) | COMPLETE
164 | 2024 |  | Planning | Update Ops Calendar | Asst Director, Operations |  | 2023-09-15 (Friday) | 2023-09-15 (Friday) | COMPLETE
165 | 2024 |  | Housing Applications and Assignments | RH Fall Application Opens | Asst Director, Operations |  | 2023-10-02 (Monday) | 2023-10-02 (Monday) | NOT STARTED
166 | 2024 |  | Student Staff Selection | Fall RA Staff Application Opens |  |  | 2023-11-01 (Wednesday) | 2023-11-01 (Wednesday) | COMPLETE
167 | 2024 |  | Housing Applications and Assignments | Room Sign Up and Apartment Marketing Begins | Marketing Manager |  | 2023-12-15 (Friday) | 2023-12-15 (Friday) | COMPLETE
168 | 2024 |  | Fall Opening | Order Tents |  |  | 2024-01-08 (Monday) | 2024-01-08 (Monday) | COMPLETE
169 | 2024 |  | Fall Opening | Order Carts/Buggies |  |  | 2024-01-08 (Monday) | 2024-01-08 (Monday) | NOT STARTED
170 | 2024 |  | Housing Applications and Assignments | RH Returning Student Room Sign-up Opens |  |  | 2024-01-17 (Wednesday) | 2024-01-17 (Wednesday) | NOT STARTED
171 | 2024 |  | Student Staff Selection | Fall RA Staff Application Closes |  |  | 2024-01-31 (Wednesday) | 2024-01-31 (Wednesday) | NOT STARTED
172 | 2024 |  | Admissions and Orientation | Admitted Students Day |  |  | 2024-02-23 (Friday) | 2024-02-23 (Friday) | NOT STARTED
173 | 2024 |  | Fall Opening | Initial Stop Drop and Go Planning and Review meeting |  |  | 2024-02-27 (Tuesday) | 2024-02-27 (Tuesday) | NOT STARTED
174 | 2024 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Final Room Change |  |  | 2024-02-27 (Tuesday) | 2024-02-27 (Tuesday) | NOT STARTED
175 | 2024 |  | Student Staff Selection | Fall RM Staff Selection Begins |  |  | 2024-03-01 (Friday) | 2024-03-01 (Friday) | NOT STARTED
176 | 2024 |  | Housing Applications and Assignments | Priority Deadline for RH Applications |  |  | 2024-03-01 (Friday) | 2024-03-01 (Friday) | NOT STARTED
177 | 2024 |  | Housing Applications and Assignments | Spring Apartment Notice to Vacate Reminder |  |  | 2024-03-01 (Friday) | 2024-03-01 (Friday) | NOT STARTED
178 | 2024 |  | Housing Applications and Assignments | RH New Student Application Deadline For First Round Room Selection (Roommate Selection, LLC Selection, Confirmation Deposit Paid) |  |  | 2024-03-01 (Friday) | 2024-03-01 (Friday) | NOT STARTED
179 | 2024 |  | Housing Applications and Assignments | LLC and Athlete Assignments |  |  | 2024-03-06 (Wednesday) | 2024-03-06 (Wednesday) | NOT STARTED
180 | 2024 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Closes |  |  | 2024-03-31 (Sunday) | 2024-03-31 (Sunday) | NOT STARTED
181 | 2024 |  | Policy and Contrtact | Apartment Lease/Policy Updates |  |  | 2024-04-01 (Monday) | 2024-04-01 (Monday) | NOT STARTED
182 | 2024 |  | Policy and Contrtact | Residence Hall Policy Updates |  |  | 2024-04-01 (Monday) | 2024-04-01 (Monday) | NOT STARTED
183 | 2024 |  | Housing Applications and Assignments | RH New Student Fall Room Assignments |  |  | 2024-04-06 (Saturday) | 2024-04-06 (Saturday) | NOT STARTED
184 | 2024 |  | Budget and Rate Development | Apartment Rate Increase Letters | Asst Director, Operations |  | 2024-05-15 (Wednesday) | 2024-05-15 (Wednesday) | NOT STARTED
185 | 2024 |  | Academic | UND Bookstore Charging Begins |  |  | 2024-06-10 (Monday) | 2024-06-10 (Monday) | NOT STARTED
186 | 2024 |  | Fall Opening | Update Move-in Web Page | Marketing Manager |  | 2024-06-14 (Friday) | 2024-06-14 (Friday) | NOT STARTED
187 | 2024 |  | Fall Opening | Move-in Scheduling Process |  |  | 2024-06-14 (Friday) | 2024-06-14 (Friday) | NOT STARTED
188 | 2024 |  | Fall Opening | Key Audits |  |  | 2024-06-24 (Monday) | 2024-07-15 (Monday) | NOT STARTED
189 | 2024 |  | Billing and Financial | Fall Bill Export |  |  | 2024-06-28 (Friday) | 2024-06-28 (Friday) | NOT STARTED
190 | 2024 |  | Academic | Fall 2024 Tuition and Fee Charges Viewable on Campus Connection |  |  | 2024-07-02 (Tuesday) | 2024-07-02 (Tuesday) | NOT STARTED
191 | 2024 |  | Academic | Current Student, 5 month payment plan opens |  |  | 2024-07-02 (Tuesday) | 2024-07-02 (Tuesday) | NOT STARTED
192 | 2024 |  | Fall Opening | Stop Drop and Go Web site and Map completed | Marketing Manager |  | 2024-07-10 (Wednesday) | 2024-07-10 (Wednesday) | NOT STARTED
193 | 2024 |  | Fall Opening | Stop Drop and Go Signage Order placed | Marketing Manager |  | 2024-07-12 (Friday) | 2024-07-12 (Friday) | NOT STARTED
194 | 2024 |  | Housing Applications and Assignments | RH Fall Early Arrival Application |  |  | 2024-07-15 (Monday) | 2024-07-15 (Monday) | NOT STARTED
195 | 2024 |  | Housing Applications and Assignments | RH New Student Spring Application |  |  | 2024-07-15 (Monday) | 2024-07-15 (Monday) | NOT STARTED
196 | 2024 |  | Admissions and Orientation | New Student Summer Orientation |  |  | 2024-07-17 (Wednesday) | 2024-07-25 (Thursday) | NOT STARTED
197 | 2024 |  | Academic | Last Day to Sign Up for a 5 month Payment Plan |  |  | 2024-07-24 (Wednesday) | 2024-07-24 (Wednesday) | NOT STARTED
198 | 2024 |  | Academic | Last day to submit family member tuition waivers For Fall |  |  | 2024-07-26 (Friday) | 2024-07-26 (Friday) | NOT STARTED
199 | 2024 |  | Billing and Financial | Apartment August Rent Export/Send Rent Reminder |  |  | 2024-07-26 (Friday) | 2024-07-26 (Friday) | NOT STARTED
200 | 2024 |  | Fall Opening | All Buildings Cleaned and Ready for Move-In |  |  | 2024-07-26 (Friday) | 2024-07-26 (Friday) | NOT STARTED
201 | 2024 |  | Academic | Summer Commencement |  |  | 2024-08-02 (Friday) | 2024-08-02 (Friday) | NOT STARTED
202 | 2024 |  | Fall Opening | Order Meal Cards for Staff working on weekend |  |  | 2024-08-06 (Tuesday) | 2024-08-06 (Tuesday) | NOT STARTED
203 | 2024 |  | Fall Opening | Coordinate Move-in Volunteers |  |  | 2024-08-06 (Tuesday) | 2024-08-06 (Tuesday) | NOT STARTED
204 | 2024 |  | Academic | Summer Commencement |  |  | 2024-08-08 (Thursday) | 2024-08-08 (Thursday) | NOT STARTED
205 | 2024 |  | Fall Opening | Residence Hall Move-in Signage Hung Up | Marketing Manager |  | 2024-08-12 (Monday) | 2024-08-12 (Monday) | NOT STARTED
206 | 2024 |  | Fall Opening | Coordinate Office Staff Weekend Coverage |  |  | 2024-08-12 (Monday) | 2024-08-12 (Monday) | NOT STARTED
207 | 2024 |  | Fall Opening | Room Inventory and Inspections |  |  | 2024-08-12 (Monday) | 2024-08-12 (Monday) | NOT STARTED
208 | 2024 |  | Campus Events | Welcome Weekend |  |  | 2024-08-23 (Friday) | 2024-08-26 (Monday) | NOT STARTED
209 | 2024 |  | Academic | Last Day to Sign Up for 4 month Payment Plan |  |  | 2024-08-24 (Saturday) | 2024-08-24 (Saturday) | NOT STARTED
210 | 2024 |  | Fall Opening | RH Official Opening Date (Saturday) |  |  | 2024-08-24 (Saturday) | 2024-08-24 (Saturday) | NOT STARTED
211 | 2024 |  | Academic | Financial Aid Consortium Agreements Due |  |  | 2024-08-26 (Monday) | 2024-08-26 (Monday) | NOT STARTED
212 | 2024 |  | Academic | ND Resident Tuition Rate Applications Due |  |  | 2024-08-26 (Monday) | 2024-08-26 (Monday) | NOT STARTED
213 | 2024 |  | Billing and Financial | Apartment September Rent Export/Send Rent Reminder |  |  | 2024-08-26 (Monday) | 2024-08-26 (Monday) | NOT STARTED
214 | 2024 |  | Academic | Fall First Full Day of Classes |  |  | 2024-08-27 (Tuesday) | 2024-08-27 (Tuesday) | NOT STARTED
215 | 2024 |  | Health and Life Safety | Residence Hall Fall Fire Drills |  |  | 2024-08-27 (Tuesday) | 2024-08-31 (Saturday) | NOT STARTED
216 | 2024 |  | Housing Applications and Assignments | Fall RH No Shows Due |  |  | 2024-08-28 (Wednesday) | 2024-08-28 (Wednesday) | NOT STARTED
217 | 2024 |  | Academic | UND Bookstore Charging Ends |  |  | 2024-08-30 (Friday) | 2024-08-30 (Friday) | NOT STARTED
218 | 2025 |  | Policy and Contrtact | RH Contract |  |  | 2024-09-01 (Sunday) | 2024-09-01 (Sunday) | NOT STARTED
219 | 2025 |  | Planning | Create Time Frames |  |  | 2024-09-01 (Sunday) | 2024-09-01 (Sunday) | NOT STARTED
220 | 2024 |  | Academic | Financial Aid Census Date |  |  | 2024-09-04 (Wednesday) | 2024-09-04 (Wednesday) | NOT STARTED
221 | 2024 |  | Academic | Fall Last Day to add or drop courses without record |  |  | 2024-09-04 (Wednesday) | 2024-09-04 (Wednesday) | NOT STARTED
222 | 2024 |  | Academic | Fall last day to submit an employee tuition waiver |  |  | 2024-09-04 (Wednesday) | 2024-09-04 (Wednesday) | NOT STARTED
223 | 2024 |  | Housing Applications and Assignments | RH Fall Room Change Begins |  |  | 2024-09-09 (Monday) | 2024-09-09 (Monday) | NOT STARTED
224 | 2024 |  | Health and Life Safety | Fall Health & Safety Checks |  |  | 2024-09-10 (Tuesday) | 2024-09-14 (Saturday) | NOT STARTED
225 | 2024 |  | Theme Meal | Potato Bowl -- Housing Program | ARH |  | 2024-09-11 (Wednesday) | 2024-09-11 (Wednesday) | NOT STARTED
226 | 2024 |  | Academic | Fall Excess Financial Aid and Scholarship Student Refunds Begin |  |  | 2024-09-11 (Wednesday) | 2024-09-11 (Wednesday) | NOT STARTED
227 | 2024 |  | Academic | Fall Charges Due (No late fee until October 15) |  |  | 2024-09-11 (Wednesday) | 2024-09-11 (Wednesday) | NOT STARTED
228 | 2024 |  | Academic | Last Day to submit incomplete work from Spring and Summer |  |  | 2024-09-13 (Friday) | 2024-09-13 (Friday) | NOT STARTED
229 | 2024 |  | Campus Events | Hawktoberfest |  |  | 2024-09-20 (Friday) | 2024-09-20 (Friday) | NOT STARTED
230 | 2024 |  | Academic | Fall Enrollment Census Date |  |  | 2024-09-23 (Monday) | 2024-09-23 (Monday) | NOT STARTED
231 | 2024 |  | Academic | Last day to sign up for 3 month payment plan |  |  | 2024-09-24 (Tuesday) | 2024-09-24 (Tuesday) | NOT STARTED
232 | 2024 |  | Campus Events | Homecoming |  |  | 2024-09-24 (Tuesday) | 2024-09-28 (Saturday) | NOT STARTED
233 | 2024 |  | Theme Meal | Homecoming Celebration -- Housing Program | ARH |  | 2024-09-26 (Thursday) | 2024-09-26 (Thursday) | NOT STARTED
234 | 2024 |  | Academic | Last day for instructors to turn in "Removal of Incomplete" form to registrar |  |  | 2024-09-27 (Friday) | 2024-09-27 (Friday) | NOT STARTED
235 | 2024 |  | Billing and Financial | Apartment October Rent Export/Send Rent Reminder |  |  | 2024-09-27 (Friday) | 2024-09-27 (Friday) | NOT STARTED
236 | 2025 |  | Housing Applications and Assignments | RH Fall Application Opens |  |  | 2024-09-30 (Monday) | 2024-09-30 (Monday) | NOT STARTED
237 | 2025 |  | Housing Applications and Assignments | RH Agreement Opens for New Student Signature |  |  | 2024-09-30 (Monday) | 2024-09-30 (Monday) | NOT STARTED
238 | 2024 |  | Housing Applications and Assignments | Fall Apartment Notice to Vacate Reminder |  |  | 2024-10-01 (Tuesday) | 2024-10-01 (Tuesday) | NOT STARTED
239 | 2024 |  | Academic | Fall Scholarship Central Applications open |  |  | 2024-10-01 (Tuesday) | 2024-10-01 (Tuesday) | NOT STARTED
240 | 2024 |  | Academic | Last day to withdraw to zero credits (regular session) for 75% refund |  |  | 2024-10-04 (Friday) | 2024-10-04 (Friday) | NOT STARTED
241 | 2024 |  | Theme Meal | Chili Challenge | Dining |  | 2024-10-07 (Monday) | 2024-10-11 (Friday) | NOT STARTED
242 | 2024 |  | Housing Applications and Assignments | Apt Fall Notice to Vacate Reminder | Apt Assignment Coordinator | Internal | 2024-10-15 (Tuesday) | 2024-10-15 (Tuesday) | NOT STARTED
243 | 2024 |  | Academic | Last day to pay Fall charges to avoid late fee |  |  | 2024-10-15 (Tuesday) | 2024-10-15 (Tuesday) | NOT STARTED
244 | 2024 |  | Admissions and Orientation | Fall Open House | Asst Director, Residential Experiences |  | 2024-10-17 (Thursday) | 2024-10-18 (Friday) | NOT STARTED
245 | 2024 |  | Theme Meal | Recipes from Home (Family Weekend) | Dining |  | 2024-10-18 (Friday) | 2024-10-20 (Sunday) | NOT STARTED
246 | 2024 |  | Admissions and Orientation | MEA/NDEA Weekend |  |  | 2024-10-18 (Friday) | 2024-10-19 (Saturday) | NOT STARTED
247 | 2024 |  | Campus Events | Family Weekend |  |  | 2024-10-18 (Friday) | 2024-10-20 (Sunday) | NOT STARTED
248 | 2025 |  | Theme Meal | Recipes from Home (Family Weekend) | Dining |  | 2024-10-18 (Friday) | 2024-10-20 (Sunday) | NOT STARTED
249 | 2024 |  | Academic | Spring Course registration date/time available in campus connection |  |  | 2024-10-25 (Friday) | 2024-10-25 (Friday) | NOT STARTED
250 | 2024 |  | Academic | Spring 2025 Course Registration Time/Date Available in Campus Connection |  |  | 2024-10-25 (Friday) | 2024-10-25 (Friday) | NOT STARTED
251 | 2024 |  | Billing and Financial | Apartment November Rent Export/Send Rent Reminder |  |  | 2024-10-28 (Monday) | 2024-10-28 (Monday) | NOT STARTED
252 | 2024 |  | Academic | Spring Semester early registration begins |  |  | 2024-10-28 (Monday) | 2024-10-28 (Monday) | NOT STARTED
253 | 2024 |  | Theme Meal | Halloween Spook-tacular Hocus Pocus Themed -- Housing Program | ARH |  | 2024-10-31 (Thursday) | 2024-10-31 (Thursday) | NOT STARTED
254 | 2024 |  | Housing Applications and Assignments | THD Roll Fall to Spring | RH Assignment Coordinator | Internal | 2024-11-01 (Friday) | 2024-11-01 (Friday) | NOT STARTED
255 | 2025 |  | Budget and Rate Development | Initial Rate Setting Completed for Admissions Cost of Attendance | Director, Finance & Facilities |  | 2024-11-01 (Friday) | 2024-11-01 (Friday) | NOT STARTED
256 | 2024 |  | Fall Closing | Fall End of Semester Communication Starts |  |  | 2024-11-01 (Friday) | 2024-11-01 (Friday) | NOT STARTED
257 | 2024 |  | Academic | Last day to withdraw to zero credits (regular session) for 50% refund |  |  | 2024-11-03 (Sunday) | 2024-11-03 (Sunday) | NOT STARTED
258 | 2024 |  | Campus Events | First Generation Student Celebration | Asst Director, Residential Experiences | Internal | 2024-11-04 (Monday) | 2024-11-08 (Friday) | NOT STARTED
259 | 2024 |  | Housing Applications and Assignments | RH End of Fall Email Communication | Asst Director, Operations | Internal | 2024-11-08 (Friday) | 2024-11-08 (Friday) | NOT STARTED
260 | 2024 |  | Housing Applications and Assignments | RH Late Dept/Semester Break App |  |  | 2024-11-08 (Friday) | 2024-12-20 (Friday) | NOT STARTED
261 | 2024 |  | Housing Applications and Assignments | RH Fall Room Cancellations |  |  | 2024-11-08 (Friday) | 2024-11-24 (Sunday) | NOT STARTED
262 | 2024 |  | Budget and Rate Development | Initial Rate Setting Completed for Admissions Cost of Attendance | Director, Finance & Facilities |  | 2024-11-10 (Sunday) | 2024-11-10 (Sunday) | NOT STARTED
263 | 2024 |  | Theme Meal | Alaska Seafood Sustainable Dinner | Dining |  | 2024-11-14 (Thursday) | 2024-11-14 (Thursday) | NOT STARTED
264 | 2024 |  | Academic | Fall Last day to change to or from S/U grading for regular session class |  |  | 2024-11-15 (Friday) | 2024-11-15 (Friday) | NOT STARTED
265 | 2024 |  | Academic | Fall Last Day to withdraw from term or drop with record |  |  | 2024-11-15 (Friday) | 2024-11-15 (Friday) | NOT STARTED
266 | 2024 |  | Fall Closing | Fall End of Semester Prints Ordered | Marketing Manager |  | 2024-11-15 (Friday) | 2024-11-29 (Friday) | NOT STARTED
267 | 2025 |  | Housing Applications and Assignments | Room Sign Up and Apartment Marketing Begins | Marketing |  | 2024-11-15 (Friday) | 2024-11-15 (Friday) | NOT STARTED
268 | 2024 |  | Campus Events | International Education Week | Asst Director, Residential Experiences | Internal | 2024-11-18 (Monday) | 2024-11-22 (Friday) | NOT STARTED
269 | 2024 |  | Housing Applications and Assignments | RH Spring Early Arrival Application |  |  | 2024-11-19 (Tuesday) | 2025-01-10 (Friday) | NOT STARTED
270 | 2024 |  | Academic | Thanksgiving Break |  |  | 2024-11-27 (Wednesday) | 2024-11-29 (Friday) | NOT STARTED
271 | 2024 |  | Billing and Financial | Apartment December Rent Export/Send Rent Reminder |  |  | 2024-11-28 (Thursday) | 2024-11-28 (Thursday) | NOT STARTED
272 | 2024 |  | Academic | Spring current student 5 month payment plan opens |  |  | 2024-12-01 (Sunday) | 2024-12-01 (Sunday) | NOT STARTED
273 | 2024 |  | Academic | Spring tuition and fee charges on campus connection |  |  | 2024-12-01 (Sunday) | 2024-12-01 (Sunday) | NOT STARTED
274 | 2025 |  | Student Staff Selection | Fall RA Staff Application Opens |  |  | 2024-12-01 (Sunday) | 2024-12-01 (Sunday) | NOT STARTED
275 | 2024 |  | Housing Applications and Assignments | RH Room Change - Fall to Spring |  |  | 2024-12-02 (Monday) | 2024-12-06 (Friday) | NOT STARTED
276 | 2024 |  | Fall Closing | Fall End of Semester Prints Distributed | Marketing Manager |  | 2024-12-02 (Monday) | 2024-12-20 (Friday) | NOT STARTED
277 | 2024 |  | Fall Closing | Fall End of Semester Communication Starts | Marketing Manager |  | 2024-12-02 (Monday) | 2024-12-20 (Friday) | NOT STARTED
278 | 2024 |  | Theme Meal | Winter Wonderland -- Housing Program | ARH |  | 2024-12-05 (Thursday) | 2024-12-05 (Thursday) | NOT STARTED
279 | 2024 |  | Academic | Fall Deadline for Undergraduates to Apply for Fall Graduation |  |  | 2024-12-06 (Friday) | 2024-12-06 (Friday) | NOT STARTED
280 | 2024 |  | Housing Applications and Assignments | RH Spring Room Assignments |  |  | 2024-12-09 (Monday) | 2024-12-11 (Wednesday) | NOT STARTED
281 | 2024 |  | Health and Life Safety | Fall End of Semester Closing Safety Checks |  |  | 2024-12-10 (Tuesday) | 2024-12-16 (Monday) | NOT STARTED
282 | 2024 |  | Billing and Financial | Spring Bill Export |  |  | 2024-12-12 (Thursday) | 2024-12-12 (Thursday) | NOT STARTED
283 | 2024 |  | Theme Meal | Moonlight Breakfast (Wilkerson Commons only) -- Housing Program | ARH |  | 2024-12-12 (Thursday) | 2024-12-12 (Thursday) | NOT STARTED
284 | 2024 |  | Academic | Fall Last Day of Classes |  |  | 2024-12-12 (Thursday) | 2024-12-12 (Thursday) | NOT STARTED
285 | 2024 |  | Academic | Spring last day to submit family member tuition waivers |  |  | 2024-12-13 (Friday) | 2024-12-13 (Friday) | NOT STARTED
286 | 2024 |  | Academic | Fall Reading and Review Day |  |  | 2024-12-13 (Friday) | 2024-12-13 (Friday) | NOT STARTED
287 | 2024 |  | Academic | Fall Finals Week |  |  | 2024-12-16 (Monday) | 2024-12-20 (Friday) | NOT STARTED
288 | 2024 |  | Academic | Fall Commencement |  |  | 2024-12-20 (Friday) | 2024-12-20 (Friday) | NOT STARTED
289 | 2024 |  | Housing Applications and Assignments | RH End of Fall Term (Sunday) |  |  | 2024-12-22 (Sunday) | 2024-12-22 (Sunday) | NOT STARTED
290 | 2024 |  | Fall Closing | Fall RH Close (Sunday) |  |  | 2024-12-22 (Sunday) | 2024-12-22 (Sunday) | NOT STARTED
291 | 2024 |  | Academic | Fall Grades Due |  |  | 2024-12-24 (Tuesday) | 2024-12-24 (Tuesday) | NOT STARTED
292 | 2024 |  | Academic | Spring last day to sing up for 5 month payment plan |  |  | 2024-12-24 (Tuesday) | 2024-12-24 (Tuesday) | NOT STARTED
293 | 2024 |  | Academic | Spring current student 4 month payment plan opens |  |  | 2024-12-25 (Wednesday) | 2024-12-25 (Wednesday) | NOT STARTED
294 | 2024 |  | Billing and Financial | Apartment January Rent Export/Send Rent Reminder |  |  | 2024-12-27 (Friday) | 2024-12-27 (Friday) | NOT STARTED
295 | 2024 |  | Camps and Conferences | Summer Conference Registration Opens | Housing Operations Manager |  | 2025-01-01 (Wednesday) | 2025-01-01 (Wednesday) | NOT STARTED
296 | 2024 |  | Housing Applications and Assignments | Fall to Spring Meal Plan Changes | Asst Director, Operations | External | 2025-01-08 (Wednesday) | 2025-01-08 (Wednesday) | NOT STARTED
297 | 2024 |  | Spring Opening | RH Spring Opening (Sunday) |  |  | 2025-01-12 (Sunday) | 2025-01-12 (Sunday) | NOT STARTED
298 | 2024 |  | Academic | Spring financial aid consortium agreements due |  |  | 2025-01-13 (Monday) | 2025-01-13 (Monday) | NOT STARTED
299 | 2024 |  | Academic | Spring ND Resident Tuition Rate applications due |  |  | 2025-01-13 (Monday) | 2025-01-13 (Monday) | NOT STARTED
300 | 2024 |  | Academic | Spring First Full Day of Classes |  |  | 2025-01-14 (Tuesday) | 2025-01-14 (Tuesday) | NOT STARTED
301 | 2024 |  | Housing Applications and Assignments | Spring RH No Shows Due |  |  | 2025-01-15 (Wednesday) | 2025-01-15 (Wednesday) | NOT STARTED
302 | 2025 |  | Housing Applications and Assignments | RH New Student Roommate Matching Opens |  |  | 2025-01-15 (Wednesday) | 2025-01-15 (Wednesday) | NOT STARTED
303 | 2024 |  | Health and Life Safety | Spring Health & Safety Safety Checks |  |  | 2025-01-21 (Tuesday) | 2025-01-25 (Saturday) | NOT STARTED
304 | 2025 |  | Housing Applications and Assignments | RH Returning Student Room Sign-up Opens |  |  | 2025-01-21 (Tuesday) | 2025-01-21 (Tuesday) | NOT STARTED
305 | 2024 |  | Academic | Spring last day to add/drop or withdraw (regular session for a 100% refund |  |  | 2025-01-23 (Thursday) | 2025-01-23 (Thursday) | NOT STARTED
306 | 2024 |  | Academic | Spring Financial Aid Census date |  |  | 2025-01-23 (Thursday) | 2025-01-23 (Thursday) | NOT STARTED
307 | 2024 |  | Academic | Spring last day to submit an employee tuition waiver |  |  | 2025-01-23 (Thursday) | 2025-01-23 (Thursday) | NOT STARTED
308 | 2024 |  | Academic | Spring Last day to sign up for 4 month payment plan |  |  | 2025-01-24 (Friday) | 2025-01-24 (Friday) | NOT STARTED
309 | 2024 |  | Academic | Spring Enrollment Census Date |  |  | 2025-01-24 (Friday) | 2025-01-24 (Friday) | NOT STARTED
310 | 2024 |  | Academic | Spring 3 month playment plan opens |  |  | 2025-01-25 (Saturday) | 2025-01-25 (Saturday) | NOT STARTED
311 | 2024 |  | Theme Meal | Wing Challenge (Wilkerson Commons) | Dining |  | 2025-01-27 (Monday) | 2025-01-31 (Friday) | NOT STARTED
312 | 2024 |  | Billing and Financial | Apartment February Rent Export/Send Rent Reminder |  |  | 2025-01-27 (Monday) | 2025-01-27 (Monday) | NOT STARTED
313 | 2024 |  | Housing Applications and Assignments | RH Spring Room Change Opens |  |  | 2025-01-27 (Monday) | 2025-01-27 (Monday) | NOT STARTED
314 | 2024 |  | Academic | Spring excess finacial aid and scholarshiop student refunds begin |  |  | 2025-01-29 (Wednesday) | 2025-01-29 (Wednesday) | NOT STARTED
315 | 2024 |  | Academic | Spring Charges Due (No late fee until March 15) |  |  | 2025-01-29 (Wednesday) | 2025-01-29 (Wednesday) | NOT STARTED
316 | 2025 |  | Fall Opening | Order Tents |  |  | 2025-01-31 (Friday) | 2025-01-31 (Friday) | NOT STARTED
317 | 2025 |  | Fall Opening | Order Carts/Buggies |  |  | 2025-01-31 (Friday) | 2025-01-31 (Friday) | NOT STARTED
318 | 2025 |  | Student Staff Selection | Fall RA Staff Application Closes |  |  | 2025-01-31 (Friday) | 2025-01-31 (Friday) | NOT STARTED
319 | 2025 |  | Student Staff Selection | Fall RM Staff Selection Begins |  |  | 2025-02-01 (Saturday) | 2025-02-01 (Saturday) | NOT STARTED
320 | 2024 |  | Theme Meal | Superbowl Party -- Housing Program | ARH |  | 2025-02-06 (Thursday) | 2025-02-06 (Thursday) | NOT STARTED
321 | 2024 |  | Recognition | Student Leadership Awards Submission Open |  |  | 2025-02-10 (Monday) | 2025-03-21 (Friday) | NOT STARTED
322 | 2025 |  | Housing Applications and Assignments | RH Returning Student Room Selection Time Emails Sent |  |  | 2025-02-10 (Monday) | 2025-02-10 (Monday) | NOT STARTED
323 | 2025 |  | Housing Applications and Assignments | RH Returning Student Open Room Selection Begins |  |  | 2025-02-12 (Wednesday) | 2025-02-19 (Wednesday) | NOT STARTED
324 | 2024 |  | Health and Life Safety | Residence Hall Spring Fire Drills |  |  | 2025-02-15 (Saturday) | 2025-02-15 (Saturday) | NOT STARTED
325 | 2024 |  | Academic | Spring last day to sign up for 3 month payment plan |  |  | 2025-02-24 (Monday) | 2025-02-24 (Monday) | NOT STARTED
326 | 2024 |  | Billing and Financial | Apartment March Rent Export/Send Rent Reminder |  |  | 2025-02-25 (Tuesday) | 2025-02-25 (Tuesday) | NOT STARTED
327 | 2025 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Final Room Change |  |  | 2025-02-27 (Thursday) | 2025-02-27 (Thursday) | NOT STARTED
328 | 2025 |  | Fall Opening | Initial Stop Drop and Go Planning and Review meeting |  |  | 2025-02-28 (Friday) | 2025-02-28 (Friday) | NOT STARTED
329 | 2025 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Closes |  |  | 2025-02-28 (Friday) | 2025-02-28 (Friday) | NOT STARTED
330 | 2024 |  | Housing Applications and Assignments | RH Summer Application |  |  | 2025-03-01 (Saturday) | 2025-03-01 (Saturday) | NOT STARTED
331 | 2025 |  | Housing Applications and Assignments | Priority Deadline for RH Applications |  |  | 2025-03-01 (Saturday) | 2025-03-01 (Saturday) | NOT STARTED
332 | 2025 |  | Housing Applications and Assignments | Spring Apartment Notice to Vacate Reminder |  |  | 2025-03-01 (Saturday) | 2025-03-01 (Saturday) | NOT STARTED
333 | 2025 |  | Housing Applications and Assignments | RH New Student Application Deadline For First Round Room Selection (Roommate Selection, LLC Selection, Confirmation Deposit Paid) |  |  | 2025-03-01 (Saturday) | 2025-03-01 (Saturday) | NOT STARTED
334 | 2024 |  | Camps and Conferences | Summer Camp/Conference Staff Selection Begins | Asst Director, Operations |  | 2025-03-03 (Monday) | 2025-03-03 (Monday) | NOT STARTED
335 | 2024 |  | Camps and Conferences | Summer Conference Sponsor Meetings Begin | Housing Operations Manager |  | 2025-03-03 (Monday) | 2025-03-03 (Monday) | NOT STARTED
336 | 2024 |  | Theme Meal | Mardi Gras Dinner -- Housing Program | ARH |  | 2025-03-04 (Tuesday) | 2025-03-04 (Tuesday) | NOT STARTED
337 | 2024 |  | Academic | Spring last day to withdraw for 75% refund |  |  | 2025-03-07 (Friday) | 2025-03-07 (Friday) | NOT STARTED
338 | 2024 |  | Academic | Spring Break |  |  | 2025-03-10 (Monday) | 2025-03-14 (Friday) | NOT STARTED
339 | 2025 |  | Housing Applications and Assignments | RH New Student Fall Room Assignments |  |  | 2025-03-10 (Monday) | 2025-04-14 (Monday) | NOT STARTED
340 | 2025 |  | Housing Applications and Assignments | LLC and Athlete Assignments |  |  | 2025-03-10 (Monday) | 2025-03-14 (Friday) | NOT STARTED
341 | 2024 |  | Academic | Spring last day to pay charges with no late fee |  |  | 2025-03-15 (Saturday) | 2025-03-15 (Saturday) | NOT STARTED
342 | 2025 |  | Admissions and Orientation | Admitted Students Day 1 |  |  | 2025-03-15 (Saturday) | 2025-03-15 (Saturday) | NOT STARTED
343 | 2024 |  | Theme Meal | Student Chopped Competition | Dining |  | 2025-03-17 (Monday) | 2025-03-20 (Thursday) | NOT STARTED
344 | 2024 |  | Billing and Financial | Apartment April Rent Export/Send Rent Reminder |  |  | 2025-03-28 (Friday) | 2025-03-28 (Friday) | NOT STARTED
345 | 2024 |  | Academic | Spring last day to withdraw for a 50% refund |  |  | 2025-04-01 (Tuesday) | 2025-04-01 (Tuesday) | NOT STARTED
346 | 2025 |  | Policy and Contrtact | Apartment Lease/Policy Updates |  |  | 2025-04-01 (Tuesday) | 2025-04-01 (Tuesday) | NOT STARTED
347 | 2025 |  | Policy and Contrtact | Residence Hall Policy Updates |  |  | 2025-04-01 (Tuesday) | 2025-04-01 (Tuesday) | NOT STARTED
348 | 2025 |  | Fall Opening | Coordinate Move-in Volunteers |  |  | 2025-04-01 (Tuesday) | 2025-04-01 (Tuesday) | NOT STARTED
349 | 2024 |  | Housing Applications and Assignments | RH Spring Room Change Closes |  |  | 2025-04-03 (Thursday) | 2025-04-03 (Thursday) | NOT STARTED
350 | 2024 |  | Academic | Spring last day to change to/from SU grading |  |  | 2025-04-11 (Friday) | 2025-04-11 (Friday) | NOT STARTED
351 | 2024 |  | Academic | Spring Last Day to withdraw from term or drop with record |  |  | 2025-04-11 (Friday) | 2025-04-11 (Friday) | NOT STARTED
352 | 2024 |  | Housing Applications and Assignments | RH Summer Room Assignments |  |  | 2025-04-14 (Monday) | 2025-04-14 (Monday) | NOT STARTED
353 | 2024 |  | Housing Applications and Assignments | Spring Late Departure |  |  | 2025-04-14 (Monday) | 2025-04-14 (Monday) | NOT STARTED
354 | 2024 |  | Spring Closing | Spring End of Semester Communication Starts | Marketing Manager |  | 2025-04-14 (Monday) | 2025-05-16 (Friday) | NOT STARTED
355 | 2024 |  | Spring Closing | Spring End of Semester Prints Ordered | Marketing Manager |  | 2025-04-14 (Monday) | 2025-04-21 (Monday) | NOT STARTED
356 | 2024 |  | Spring Closing | RollOff Dumpsters for RHs and Apartments |  |  | 2025-04-15 (Tuesday) | 2025-04-15 (Tuesday) | NOT STARTED
357 | 2024 |  | Spring Closing | Bicycle Apandoned Property Process |  |  | 2025-04-15 (Tuesday) | 2025-04-15 (Tuesday) | NOT STARTED
358 | 2024 |  | Housing Applications and Assignments | Apartment Summer Assignment Rolls |  |  | 2025-04-15 (Tuesday) | 2025-04-15 (Tuesday) | NOT STARTED
359 | 2025 |  | Admissions and Orientation | Admitted Students Day 2 |  |  | 2025-04-15 (Tuesday) | 2025-04-15 (Tuesday) | NOT STARTED
360 | 2024 |  | Theme Meal | Time-Out Week Menu | Dining |  | 2025-04-17 (Thursday) | 2025-04-17 (Thursday) | NOT STARTED
361 | 2024 |  | Academic | Easter Break |  |  | 2025-04-18 (Friday) | 2025-04-21 (Monday) | NOT STARTED
362 | 2024 |  | Spring Closing | Spring End of Semester Prints Distributed | Marketing Manager |  | 2025-04-21 (Monday) | 2025-04-21 (Monday) | NOT STARTED
363 | 2024 |  | Theme Meal | Celebrate Earth Day | Dining |  | 2025-04-22 (Tuesday) | 2025-04-22 (Tuesday) | NOT STARTED
364 | 2024 |  | Billing and Financial | Apartment May Rent Export/Send Rent Reminder |  |  | 2025-04-25 (Friday) | 2025-04-25 (Friday) | NOT STARTED
365 | 2024 |  | Recognition | Student Leadership Award Ceremony |  |  | 2025-04-25 (Friday) | 2025-04-25 (Friday) | NOT STARTED
366 | 2024 |  | Billing and Financial | Summer Bill Export |  |  | 2025-04-30 (Wednesday) | 2025-04-30 (Wednesday) | NOT STARTED
367 | 2024 |  | Theme Meal | Star Wars Theme Dinner | Dining |  | 2025-05-04 (Sunday) | 2025-05-04 (Sunday) | NOT STARTED
368 | 2024 |  | Theme Meal | Moonlight Pizza -- Housing Program | ARH |  | 2025-05-08 (Thursday) | 2025-05-08 (Thursday) | NOT STARTED
369 | 2024 |  | Academic | Spring last day of classes |  |  | 2025-05-08 (Thursday) | 2025-05-08 (Thursday) | NOT STARTED
370 | 2024 |  | Academic | Spring Reading and Review Day |  |  | 2025-05-09 (Friday) | 2025-05-09 (Friday) | NOT STARTED
371 | 2024 |  | Health and Life Safety | Spring Closing Safety Checks |  |  | 2025-05-10 (Saturday) | 2025-05-12 (Monday) | NOT STARTED
372 | 2024 |  | Academic | Spring Finals Week |  |  | 2025-05-12 (Monday) | 2025-05-16 (Friday) | NOT STARTED
373 | 2024 |  | Health and Life Safety | Summer Health & Safety Checks |  |  | 2025-05-14 (Wednesday) | 2025-05-14 (Wednesday) | NOT STARTED
374 | 2025 |  | Budget and Rate Development | Apartment Rate Increase Letters | Assistant Director of Operations |  | 2025-05-15 (Thursday) | 2025-05-15 (Thursday) | NOT STARTED
375 | 2024 |  | Spring Closing | Spring RH Close (Saturday) |  |  | 2025-05-17 (Saturday) | 2025-05-17 (Saturday) | NOT STARTED
376 | 2024 |  | Academic | Spring Commencement |  |  | 2025-05-17 (Saturday) | 2025-05-17 (Saturday) | NOT STARTED
377 | 2024 |  | Summer Opening | RH Summer Halls Open |  |  | 2025-05-18 (Sunday) | 2025-05-18 (Sunday) | NOT STARTED
378 | 2024 |  | Health and Life Safety | Residence Hall Summer Fire Drills |  |  | 2025-05-19 (Monday) | 2025-05-23 (Friday) | NOT STARTED
379 | 2024 |  | Academic | Summer First Day of Classes |  |  | 2025-05-19 (Monday) | 2025-05-19 (Monday) | NOT STARTED
380 | 2024 |  | Academic | Spring Grades Due |  |  | 2025-05-21 (Wednesday) | 2025-05-21 (Wednesday) | NOT STARTED
381 | 2024 |  | Camps and Conferences | Summer Guest Housing Opens (Swanson) | Housing Operations Manager |  | 2025-05-26 (Monday) | 2025-05-26 (Monday) | NOT STARTED
382 | 2024 |  | Billing and Financial | Apartment June Rent Export/Send Rent Reminder |  |  | 2025-05-26 (Monday) | 2025-05-26 (Monday) | NOT STARTED
383 | 2024 |  | Professional Development | Student Affairs Division Mid-Year Meeting | Director, Housing & Res Life | Internal | 2025-05-27 (Tuesday) | 2025-05-29 (Thursday) | NOT STARTED
384 | 2025 |  | Fall Opening | Update Move-in Web Page | Marketing |  | 2025-06-01 (Sunday) | 2025-06-01 (Sunday) | NOT STARTED
385 | 2025 |  | Academic | UND Bookstore Charging Begins |  |  | 2025-06-10 (Tuesday) | 2025-06-10 (Tuesday) | NOT STARTED
386 | 2025 |  | Fall Opening | Move-in Scheduling Process |  |  | 2025-06-15 (Sunday) | 2025-06-15 (Sunday) | NOT STARTED
387 | 2024 |  | Billing and Financial | Apartment July Rent Export/Send Rent Reminder |  |  | 2025-06-27 (Friday) | 2025-06-27 (Friday) | NOT STARTED
388 | 2025 |  | Housing Applications and Assignments | RH Fall Early Arrival Application |  |  | 2025-07-01 (Tuesday) | 2025-07-01 (Tuesday) | NOT STARTED
389 | 2025 |  | Housing Applications and Assignments | RH New Student Spring Application | RH Assignment Coordinator |  | 2025-07-01 (Tuesday) | 2025-07-01 (Tuesday) | NOT STARTED
390 | 2025 |  | Academic | Fall 2024 Tuition and Fee Charges Viewable on Campus Connection |  |  | 2025-07-02 (Wednesday) | 2025-07-02 (Wednesday) | NOT STARTED
391 | 2025 |  | Academic | Current Student, 5 month payment plan opens |  |  | 2025-07-02 (Wednesday) | 2025-07-02 (Wednesday) | NOT STARTED
392 | 2025 |  | Fall Opening | Stop Drop and Go Web site and Map completed | Marketing |  | 2025-07-03 (Thursday) | 2025-07-03 (Thursday) | NOT STARTED
393 | 2025 |  | Fall Opening | Stop Drop and Go Signage Order placed | Marketing |  | 2025-07-11 (Friday) | 2025-07-11 (Friday) | NOT STARTED
394 | 2025 |  | Admissions and Orientation | New Student Summer Orientation |  |  | 2025-07-17 (Thursday) | 2025-07-25 (Friday) | NOT STARTED
395 | 2025 |  | Academic | Last Day to Sign Up for a 5 month Payment Plan |  |  | 2025-07-24 (Thursday) | 2025-07-24 (Thursday) | NOT STARTED
396 | 2025 |  | Academic | Last day to submit family member tuition waivers For Fall |  |  | 2025-07-26 (Saturday) | 2025-07-26 (Saturday) | NOT STARTED
397 | 2025 |  | Fall Opening | All Buildings Cleaned and Ready for Move-In |  |  | 2025-08-01 (Friday) | 2025-08-01 (Friday) | NOT STARTED
398 | 2025 |  | Fall Opening | Coordinate Office Staff Weekend Coverage |  |  | 2025-08-01 (Friday) | 2025-08-01 (Friday) | NOT STARTED
399 | 2025 |  | Academic | Summer Commencement |  |  | 2025-08-02 (Saturday) | 2025-08-02 (Saturday) | NOT STARTED
400 | 2024 |  | Summer Closing | RH Summer Hall Closes (Sunday) |  |  | 2025-08-05 (Tuesday) | 2025-08-05 (Tuesday) | NOT STARTED
401 | 2025 |  | Fall Opening | Order Meal Cards for Staff working on weekend |  |  | 2025-08-07 (Thursday) | 2025-08-07 (Thursday) | NOT STARTED
402 | 2025 |  | Fall Opening | Key Audits |  |  | 2025-08-08 (Friday) | 2025-08-08 (Friday) | NOT STARTED
403 | 2025 |  | Academic | Summer Commencement |  |  | 2025-08-08 (Friday) | 2025-08-08 (Friday) | NOT STARTED
404 | 2025 |  | Fall Opening | Room Inventory and Inspections |  |  | 2025-08-13 (Wednesday) | 2025-08-13 (Wednesday) | NOT STARTED
405 | 2025 |  | Fall Opening | Residence Hall Move-in Signage Hung Up | Marketing |  | 2025-08-15 (Friday) | 2025-08-15 (Friday) | NOT STARTED
406 | 2025 |  | Campus Events | Welcome Weekend |  |  | 2025-08-23 (Saturday) | 2025-08-24 (Sunday) | NOT STARTED
407 | 2025 |  | Fall Opening | RH Official Opening Date (Saturday) |  |  | 2025-08-23 (Saturday) | 2025-08-23 (Saturday) | NOT STARTED
408 | 2025 |  | Academic | Last Day to Sign Up for 4 month Payment Plan |  |  | 2025-08-24 (Sunday) | 2025-08-24 (Sunday) | NOT STARTED
409 | 2025 |  | Academic | Financial Aid Consortium Agreements Due |  |  | 2025-08-26 (Tuesday) | 2025-08-26 (Tuesday) | NOT STARTED
410 | 2025 |  | Academic | ND Resident Tuition Rate Applications Due |  |  | 2025-08-26 (Tuesday) | 2025-08-26 (Tuesday) | NOT STARTED
411 | 2025 |  | Housing Applications and Assignments | Fall RH No Shows Due |  |  | 2025-08-27 (Wednesday) | 2025-08-27 (Wednesday) | NOT STARTED
412 | 2025 |  | Academic | Fall First Full Day of Classes |  |  | 2025-08-27 (Wednesday) | 2025-08-27 (Wednesday) | NOT STARTED
413 | 2025 |  | Academic | UND Bookstore Charging Ends |  |  | 2025-08-30 (Saturday) | 2025-08-30 (Saturday) | NOT STARTED
414 | 2026 |  | Policy and Contrtact | RH Contract |  |  | 2025-09-01 (Monday) | 2025-09-01 (Monday) | NOT STARTED
415 | 2026 |  | Planning | Create Time Frames |  |  | 2025-09-01 (Monday) | 2025-09-01 (Monday) | NOT STARTED
416 | 2025 |  | Academic | Financial Aid Census Date |  |  | 2025-09-04 (Thursday) | 2025-09-04 (Thursday) | NOT STARTED
417 | 2025 |  | Academic | Fall Last Day to add or drop courses without record |  |  | 2025-09-04 (Thursday) | 2025-09-04 (Thursday) | NOT STARTED
418 | 2025 |  | Academic | Fall last day to submit an employee tuition waiver |  |  | 2025-09-04 (Thursday) | 2025-09-04 (Thursday) | NOT STARTED
419 | 2025 |  | Housing Applications and Assignments | RH Fall Room Change Begins |  |  | 2025-09-08 (Monday) | 2025-09-08 (Monday) | NOT STARTED
420 | 2025 |  | Academic | Fall Excess Financial Aid and Scholarship Student Refunds Begin |  |  | 2025-09-11 (Thursday) | 2025-09-11 (Thursday) | NOT STARTED
421 | 2025 |  | Academic | Fall Charges Due (No late fee until October 15) |  |  | 2025-09-11 (Thursday) | 2025-09-11 (Thursday) | NOT STARTED
422 | 2025 |  | Academic | Last Day to submit incomplete work from Spring and Summer |  |  | 2025-09-13 (Saturday) | 2025-09-13 (Saturday) | NOT STARTED
423 | 2025 |  | Campus Events | Homecoming |  |  | 2025-09-15 (Monday) | 2025-09-20 (Saturday) | NOT STARTED
424 | 2025 |  | Campus Events | Hawktoberfest |  |  | 2025-09-19 (Friday) | 2025-09-19 (Friday) | NOT STARTED
425 | 2025 |  | Academic | Fall Enrollment Census Date |  |  | 2025-09-23 (Tuesday) | 2025-09-23 (Tuesday) | NOT STARTED
426 | 2025 |  | Academic | Last day to sign up for 3 month payment plan |  |  | 2025-09-24 (Wednesday) | 2025-09-24 (Wednesday) | NOT STARTED
427 | 2025 |  | Academic | Last day for instructors to turn in "Removal of Incomplete" form to registrar |  |  | 2025-09-27 (Saturday) | 2025-09-27 (Saturday) | NOT STARTED
428 | 2026 |  | Housing Applications and Assignments | RH Fall Application Opens |  |  | 2025-09-30 (Tuesday) | 2025-09-30 (Tuesday) | NOT STARTED
429 | 2025 |  | Housing Applications and Assignments | Fall Apartment Notice to Vacate Reminder |  |  | 2025-10-01 (Wednesday) | 2025-10-01 (Wednesday) | NOT STARTED
430 | 2025 |  | Academic | Fall Scholarship Central Applications open |  |  | 2025-10-01 (Wednesday) | 2025-10-01 (Wednesday) | NOT STARTED
431 | 2025 |  | Academic | Last day to withdraw to zero credits (regular session) for 75% refund |  |  | 2025-10-04 (Saturday) | 2025-10-04 (Saturday) | NOT STARTED
432 | 2026 | nan | Housing Applications and Assignments | RH Agreement Opens for New Student | Assistant Director of Operations | External | 2025-10-06 (Monday) | 2025-10-06 (Monday) | IN PROGRESS
433 | 2025 |  | Campus Events | Family Weekend |  |  | 2025-10-10 (Friday) | 2025-10-12 (Sunday) | NOT STARTED
434 | 2025 |  | Academic | Last day to pay Fall charges to avoid late fee |  |  | 2025-10-15 (Wednesday) | 2025-10-15 (Wednesday) | NOT STARTED
435 | 2025 |  | Admissions and Orientation | MEA/NDEA Weekend |  |  | 2025-10-17 (Friday) | 2025-10-18 (Saturday) | NOT STARTED
436 | 2026 |  | Theme Meal | Recipes from Home (Family Weekend) | Dining |  | 2025-10-18 (Saturday) | 2025-10-20 (Monday) | NOT STARTED
437 | 2025 |  | Academic | Spring Course registration date/time available in campus connection |  |  | 2025-10-25 (Saturday) | 2025-10-25 (Saturday) | NOT STARTED
438 | 2025 |  | Academic | Spring 2025 Course Registration Time/Date Available in Campus Connection |  |  | 2025-10-25 (Saturday) | 2025-10-25 (Saturday) | NOT STARTED
439 | 2025 |  | Academic | Spring Semester early registration begins |  |  | 2025-10-28 (Tuesday) | 2025-10-28 (Tuesday) | NOT STARTED
440 | 2025 |  | Fall Closing | Fall End of Semester Communication Starts |  |  | 2025-11-01 (Saturday) | 2025-11-01 (Saturday) | NOT STARTED
441 | 2026 |  | Budget and Rate Development | Initial Rate Setting Completed for Admissions Cost of Attendance | Director, Finance & Facilities |  | 2025-11-01 (Saturday) | 2025-11-01 (Saturday) | NOT STARTED
442 | 2025 |  | Academic | Last day to withdraw to zero credits (regular session) for 50% refund |  |  | 2025-11-03 (Monday) | 2025-11-03 (Monday) | NOT STARTED
443 | 2025 |  | Campus Events | First Generation Student Celebration | Asst Director, Residential Experiences | Internal | 2025-11-03 (Monday) | 2025-11-07 (Friday) | NOT STARTED
444 | 2025 |  | Housing Applications and Assignments | RH Fall Room Cancellations |  |  | 2025-11-09 (Sunday) | 2025-11-09 (Sunday) | NOT STARTED
445 | 2025 |  | Housing Applications and Assignments | RH Late Dept/Semester Break App |  |  | 2025-11-09 (Sunday) | 2025-12-21 (Sunday) | NOT STARTED
446 | 2026 |  | Housing Applications and Assignments | Room Sign Up and Apartment Marketing Begins | Marketing |  | 2025-11-15 (Saturday) | 2025-11-15 (Saturday) | NOT STARTED
447 | 2025 |  | Academic | Fall Last day to change to or from S/U grading for regular session class |  |  | 2025-11-15 (Saturday) | 2025-11-15 (Saturday) | NOT STARTED
448 | 2025 |  | Academic | Fall Last Day to withdraw from term or drop with record |  |  | 2025-11-15 (Saturday) | 2025-11-15 (Saturday) | NOT STARTED
449 | 2025 |  | Campus Events | International Education Week | Asst Director, Residential Experiences | Internal | 2025-11-17 (Monday) | 2025-11-21 (Friday) | NOT STARTED
450 | 2025 |  | Housing Applications and Assignments | RH Spring Early Arrival Application |  |  | 2025-11-18 (Tuesday) | 2025-11-18 (Tuesday) | NOT STARTED
451 | 2025 |  | Academic | Thanksgiving Break |  |  | 2025-11-27 (Thursday) | 2025-11-29 (Saturday) | NOT STARTED
452 | 2025 |  | Housing Applications and Assignments | RH Room Change - Fall to Spring |  |  | 2025-12-01 (Monday) | 2025-12-05 (Friday) | NOT STARTED
453 | 2026 |  | Student Staff Selection | Fall RA Staff Application Opens |  |  | 2025-12-01 (Monday) | 2025-12-01 (Monday) | NOT STARTED
454 | 2025 |  | Academic | Spring current student 5 month payment plan opens |  |  | 2025-12-01 (Monday) | 2025-12-01 (Monday) | NOT STARTED
455 | 2025 |  | Academic | Spring tuition and fee charges on campus connection |  |  | 2025-12-01 (Monday) | 2025-12-01 (Monday) | NOT STARTED
456 | 2025 |  | Academic | Fall Deadline for Undergraduates to Apply for Fall Graduation |  |  | 2025-12-06 (Saturday) | 2025-12-06 (Saturday) | NOT STARTED
457 | 2025 |  | Housing Applications and Assignments | RH Spring Room Assignments |  |  | 2025-12-08 (Monday) | 2025-12-10 (Wednesday) | NOT STARTED
458 | 2025 |  | Theme Meal | Moonlight Breakfast (Wilkerson Commons only) -- Housing Program | Marketing/ARH |  | 2025-12-11 (Thursday) | 2025-12-11 (Thursday) | NOT STARTED
459 | 2025 |  | Academic | Fall Last Day of Classes |  |  | 2025-12-12 (Friday) | 2025-12-12 (Friday) | NOT STARTED
460 | 2025 |  | Academic | Spring last day to submit family member tuition waivers |  |  | 2025-12-13 (Saturday) | 2025-12-13 (Saturday) | NOT STARTED
461 | 2025 |  | Academic | Fall Reading and Review Day |  |  | 2025-12-13 (Saturday) | 2025-12-13 (Saturday) | NOT STARTED
462 | 2025 |  | Academic | Fall Finals Week |  |  | 2025-12-16 (Tuesday) | 2025-12-20 (Saturday) | NOT STARTED
463 | 2025 |  | Academic | Fall Commencement |  |  | 2025-12-20 (Saturday) | 2025-12-20 (Saturday) | NOT STARTED
464 | 2025 |  | Housing Applications and Assignments | RH End of Fall Term (Sunday) |  |  | 2025-12-21 (Sunday) | 2025-12-21 (Sunday) | NOT STARTED
465 | 2025 |  | Fall Closing | Fall RH Close (Sunday) |  |  | 2025-12-21 (Sunday) | 2025-12-21 (Sunday) | NOT STARTED
466 | 2025 |  | Academic | Fall Grades Due |  |  | 2025-12-24 (Wednesday) | 2025-12-24 (Wednesday) | NOT STARTED
467 | 2025 |  | Academic | Spring last day to sing up for 5 month payment plan |  |  | 2025-12-24 (Wednesday) | 2025-12-24 (Wednesday) | NOT STARTED
468 | 2025 |  | Academic | Spring current student 4 month payment plan opens |  |  | 2025-12-25 (Thursday) | 2025-12-25 (Thursday) | NOT STARTED
469 | 2025 |  | Spring Opening | RH Spring Opening (Sunday) |  |  | 2026-01-11 (Sunday) | 2026-01-11 (Sunday) | NOT STARTED
470 | 2025 |  | Academic | Spring financial aid consortium agreements due |  |  | 2026-01-13 (Tuesday) | 2026-01-13 (Tuesday) | NOT STARTED
471 | 2025 |  | Academic | Spring ND Resident Tuition Rate applications due |  |  | 2026-01-13 (Tuesday) | 2026-01-13 (Tuesday) | NOT STARTED
472 | 2025 |  | Academic | Spring First Full Day of Classes |  |  | 2026-01-14 (Wednesday) | 2026-01-14 (Wednesday) | NOT STARTED
473 | 2025 |  | Housing Applications and Assignments | Spring RH No Shows Due |  |  | 2026-01-15 (Thursday) | 2026-01-15 (Thursday) | NOT STARTED
474 | 2026 |  | Housing Applications and Assignments | RH New Student Roommate Matching Opens |  |  | 2026-01-15 (Thursday) | 2026-01-15 (Thursday) | NOT STARTED
475 | 2026 |  | Housing Applications and Assignments | RH Returning Student Room Sign-up Opens |  |  | 2026-01-21 (Wednesday) | 2026-01-21 (Wednesday) | NOT STARTED
476 | 2025 |  | Academic | Spring last day to add/drop or withdraw (regular session for a 100% refund |  |  | 2026-01-23 (Friday) | 2026-01-23 (Friday) | NOT STARTED
477 | 2025 |  | Academic | Spring Financial Aid Census date |  |  | 2026-01-23 (Friday) | 2026-01-23 (Friday) | NOT STARTED
478 | 2025 |  | Academic | Spring last day to submit an employee tuition waiver |  |  | 2026-01-23 (Friday) | 2026-01-23 (Friday) | NOT STARTED
479 | 2025 |  | Academic | Spring Last day to sign up for 4 month payment plan |  |  | 2026-01-24 (Saturday) | 2026-01-24 (Saturday) | NOT STARTED
480 | 2025 |  | Academic | Spring Enrollment Census Date |  |  | 2026-01-24 (Saturday) | 2026-01-24 (Saturday) | NOT STARTED
481 | 2025 |  | Academic | Spring 3 month playment plan opens |  |  | 2026-01-25 (Sunday) | 2026-01-25 (Sunday) | NOT STARTED
482 | 2025 |  | Housing Applications and Assignments | RH Spring Room Change Opens |  |  | 2026-01-26 (Monday) | 2026-01-26 (Monday) | NOT STARTED
483 | 2025 |  | Academic | Spring excess finacial aid and scholarshiop student refunds begin |  |  | 2026-01-29 (Thursday) | 2026-01-29 (Thursday) | NOT STARTED
484 | 2025 |  | Academic | Spring Charges Due (No late fee until March 15) |  |  | 2026-01-29 (Thursday) | 2026-01-29 (Thursday) | NOT STARTED
485 | 2026 |  | Fall Opening | Order Tents |  |  | 2026-01-31 (Saturday) | 2026-01-31 (Saturday) | NOT STARTED
486 | 2026 |  | Fall Opening | Order Carts/Buggies |  |  | 2026-01-31 (Saturday) | 2026-01-31 (Saturday) | NOT STARTED
487 | 2026 |  | Student Staff Selection | Fall RA Staff Application Closes |  |  | 2026-01-31 (Saturday) | 2026-01-31 (Saturday) | NOT STARTED
488 | 2026 |  | Student Staff Selection | Fall RM Staff Selection Begins |  |  | 2026-02-01 (Sunday) | 2026-02-01 (Sunday) | NOT STARTED
489 | 2026 |  | Housing Applications and Assignments | RH Returning Student Room Selection Time Emails Sent |  |  | 2026-02-10 (Tuesday) | 2026-02-10 (Tuesday) | NOT STARTED
490 | 2026 |  | Housing Applications and Assignments | RH Returning Student Open Room Selection Begins |  |  | 2026-02-12 (Thursday) | 2026-02-19 (Thursday) | NOT STARTED
491 | 2025 |  | Academic | Spring last day to sign up for 3 month payment plan |  |  | 2026-02-24 (Tuesday) | 2026-02-24 (Tuesday) | NOT STARTED
492 | 2026 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Final Room Change |  |  | 2026-02-27 (Friday) | 2026-02-27 (Friday) | NOT STARTED
493 | 2026 |  | Fall Opening | Initial Stop Drop and Go Planning and Review meeting |  |  | 2026-02-28 (Saturday) | 2026-02-28 (Saturday) | NOT STARTED
494 | 2026 |  | Housing Applications and Assignments | RH Returning Student Room Sign-Up Closes |  |  | 2026-02-28 (Saturday) | 2026-02-28 (Saturday) | NOT STARTED
495 | 2025 |  | Housing Applications and Assignments | RH Summer Application |  |  | 2026-03-01 (Sunday) | 2026-03-01 (Sunday) | NOT STARTED
496 | 2026 |  | Housing Applications and Assignments | Priority Deadline for RH Applications |  |  | 2026-03-01 (Sunday) | 2026-03-01 (Sunday) | NOT STARTED
497 | 2026 |  | Housing Applications and Assignments | Spring Apartment Notice to Vacate Reminder |  |  | 2026-03-01 (Sunday) | 2026-03-01 (Sunday) | NOT STARTED
498 | 2026 |  | Housing Applications and Assignments | RH New Student Application Deadline For First Round Room Selection (Roommate Selection, LLC Selection, Confirmation Deposit Paid) |  |  | 2026-03-01 (Sunday) | 2026-03-01 (Sunday) | NOT STARTED
499 | 2025 |  | Academic | Spring last day to withdraw for 75% refund |  |  | 2026-03-07 (Saturday) | 2026-03-07 (Saturday) | NOT STARTED
500 | 2026 |  | Housing Applications and Assignments | RH New Student Fall Room Assignments |  |  | 2026-03-10 (Tuesday) | 2026-04-14 (Tuesday) | NOT STARTED
501 | 2026 |  | Housing Applications and Assignments | LLC and Athlete Assignments |  |  | 2026-03-10 (Tuesday) | 2026-03-14 (Saturday) | NOT STARTED
502 | 2025 |  | Academic | Spring Break |  |  | 2026-03-10 (Tuesday) | 2026-03-14 (Saturday) | NOT STARTED
503 | 2026 |  | Admissions and Orientation | Admitted Students Day 1 |  |  | 2026-03-15 (Sunday) | 2026-03-15 (Sunday) | NOT STARTED
504 | 2025 |  | Academic | Spring last day to pay charges with no late fee |  |  | 2026-03-15 (Sunday) | 2026-03-15 (Sunday) | NOT STARTED
505 | 2026 |  | Policy and Contrtact | Apartment Lease/Policy Updates |  |  | 2026-04-01 (Wednesday) | 2026-04-01 (Wednesday) | NOT STARTED
506 | 2026 |  | Policy and Contrtact | Residence Hall Policy Updates |  |  | 2026-04-01 (Wednesday) | 2026-04-01 (Wednesday) | NOT STARTED
507 | 2026 |  | Fall Opening | Coordinate Move-in Volunteers |  |  | 2026-04-01 (Wednesday) | 2026-04-01 (Wednesday) | NOT STARTED
508 | 2025 |  | Academic | Spring last day to withdraw for a 50% refund |  |  | 2026-04-01 (Wednesday) | 2026-04-01 (Wednesday) | NOT STARTED
509 | 2025 |  | Housing Applications and Assignments | RH Spring Room Change Closes |  |  | 2026-04-03 (Friday) | 2026-04-03 (Friday) | NOT STARTED
510 | 2025 |  | Academic | Spring last day to change to/from SU grading |  |  | 2026-04-11 (Saturday) | 2026-04-11 (Saturday) | NOT STARTED
511 | 2025 |  | Academic | Spring Last Day to withdraw from term or drop with record |  |  | 2026-04-11 (Saturday) | 2026-04-11 (Saturday) | NOT STARTED
512 | 2025 |  | Housing Applications and Assignments | Spring Late Departure |  |  | 2026-04-14 (Tuesday) | 2026-04-14 (Tuesday) | NOT STARTED
513 | 2025 |  | Housing Applications and Assignments | RH Summer Room Assignments |  |  | 2026-04-14 (Tuesday) | 2026-04-14 (Tuesday) | NOT STARTED
514 | 2025 |  | Housing Applications and Assignments | Apartment Summer Assignment Rolls |  |  | 2026-04-15 (Wednesday) | 2026-04-15 (Wednesday) | NOT STARTED
515 | 2025 |  | Spring Closing | RollOff Dumpsters for RHs and Apartments |  |  | 2026-04-15 (Wednesday) | 2026-04-15 (Wednesday) | NOT STARTED
516 | 2025 |  | Spring Closing | Bicycle Apandoned Property Process |  |  | 2026-04-15 (Wednesday) | 2026-04-15 (Wednesday) | NOT STARTED
517 | 2026 |  | Admissions and Orientation | Admitted Students Day 2 |  |  | 2026-04-15 (Wednesday) | 2026-04-15 (Wednesday) | NOT STARTED
518 | 2025 |  | Academic | Easter Break |  |  | 2026-04-18 (Saturday) | 2026-04-21 (Tuesday) | NOT STARTED
519 | 2025 |  | Theme Meal | Moonlight Pizza -- Housing Program | Marketing/ARH |  | 2026-05-07 (Thursday) | 2026-05-07 (Thursday) | NOT STARTED
520 | 2025 |  | Academic | Spring last day of classes |  |  | 2026-05-08 (Friday) | 2026-05-08 (Friday) | NOT STARTED
521 | 2025 |  | Academic | Spring Reading and Review Day |  |  | 2026-05-09 (Saturday) | 2026-05-09 (Saturday) | NOT STARTED
522 | 2025 |  | Academic | Spring Finals Week |  |  | 2026-05-12 (Tuesday) | 2026-05-16 (Saturday) | NOT STARTED
523 | 2026 |  | Budget and Rate Development | Apartment Rate Increase Letters | Assistant Director of Operations |  | 2026-05-15 (Friday) | 2026-05-15 (Friday) | NOT STARTED
524 | 2025 |  | Spring Closing | Spring RH Close (Saturday) |  |  | 2026-05-16 (Saturday) | 2026-05-16 (Saturday) | NOT STARTED
525 | 2025 |  | Summer Opening | RH Summer Halls Open |  |  | 2026-05-17 (Sunday) | 2026-05-17 (Sunday) | NOT STARTED
526 | 2025 |  | Academic | Spring Commencement |  |  | 2026-05-17 (Sunday) | 2026-05-17 (Sunday) | NOT STARTED
527 | 2025 |  | Academic | Summer First Day of Classes |  |  | 2026-05-19 (Tuesday) | 2026-05-19 (Tuesday) | NOT STARTED
528 | 2025 |  | Academic | Spring Grades Due |  |  | 2026-05-21 (Thursday) | 2026-05-21 (Thursday) | NOT STARTED
529 | 2026 |  | Fall Opening | Update Move-in Web Page | Marketing |  | 2026-06-01 (Monday) | 2026-06-01 (Monday) | NOT STARTED
530 | 2026 |  | Academic | UND Bookstore Charging Begins |  |  | 2026-06-10 (Wednesday) | 2026-06-10 (Wednesday) | NOT STARTED
531 | 2026 |  | Fall Opening | Move-in Scheduling Process |  |  | 2026-06-15 (Monday) | 2026-06-15 (Monday) | NOT STARTED
532 | 2026 |  | Housing Applications and Assignments | RH Fall Early Arrival Application |  |  | 2026-07-01 (Wednesday) | 2026-07-01 (Wednesday) | NOT STARTED
533 | 2026 |  | Academic | Fall 2024 Tuition and Fee Charges Viewable on Campus Connection |  |  | 2026-07-02 (Thursday) | 2026-07-02 (Thursday) | NOT STARTED
534 | 2026 |  | Academic | Current Student, 5 month payment plan opens |  |  | 2026-07-02 (Thursday) | 2026-07-02 (Thursday) | NOT STARTED
535 | 2026 |  | Fall Opening | Stop Drop and Go Web site and Map completed | Marketing |  | 2026-07-03 (Friday) | 2026-07-03 (Friday) | NOT STARTED
536 | 2026 |  | Fall Opening | Stop Drop and Go Signage Order placed | Marketing |  | 2026-07-11 (Saturday) | 2026-07-11 (Saturday) | NOT STARTED
537 | 2026 |  | Housing Applications and Assignments | RH New Student Spring Application |  |  | 2026-07-15 (Wednesday) | 2026-07-15 (Wednesday) | NOT STARTED
538 | 2026 |  | Admissions and Orientation | New Student Summer Orientation |  |  | 2026-07-17 (Friday) | 2026-07-25 (Saturday) | NOT STARTED
539 | 2026 |  | Academic | Last Day to Sign Up for a 5 month Payment Plan |  |  | 2026-07-24 (Friday) | 2026-07-24 (Friday) | NOT STARTED
540 | 2026 |  | Academic | Last day to submit family member tuition waivers For Fall |  |  | 2026-07-26 (Sunday) | 2026-07-26 (Sunday) | NOT STARTED
541 | 2026 |  | Fall Opening | All Buildings Cleaned and Ready for Move-In |  |  | 2026-08-01 (Saturday) | 2026-08-01 (Saturday) | NOT STARTED
542 | 2026 |  | Fall Opening | Coordinate Office Staff Weekend Coverage |  |  | 2026-08-01 (Saturday) | 2026-08-01 (Saturday) | NOT STARTED
543 | 2026 |  | Academic | Summer Commencement |  |  | 2026-08-02 (Sunday) | 2026-08-02 (Sunday) | NOT STARTED
544 | 2025 |  | Summer Closing | RH Summer Hall Closes (Sunday) |  |  | 2026-08-04 (Tuesday) | 2026-08-04 (Tuesday) | NOT STARTED
545 | 2026 |  | Fall Opening | Order Meal Cards for Staff working on weekend |  |  | 2026-08-07 (Friday) | 2026-08-07 (Friday) | NOT STARTED
546 | 2026 |  | Fall Opening | Key Audits |  |  | 2026-08-08 (Saturday) | 2026-08-08 (Saturday) | NOT STARTED
547 | 2026 |  | Academic | Summer Commencement |  |  | 2026-08-08 (Saturday) | 2026-08-08 (Saturday) | NOT STARTED
548 | 2026 |  | Fall Opening | Room Inventory and Inspections |  |  | 2026-08-13 (Thursday) | 2026-08-13 (Thursday) | NOT STARTED
549 | 2026 |  | Fall Opening | Residence Hall Move-in Signage Hung Up | Marketing |  | 2026-08-15 (Saturday) | 2026-08-15 (Saturday) | NOT STARTED
550 | 2026 |  | Campus Events | Welcome Weekend |  |  | 2026-08-23 (Sunday) | 2026-08-24 (Monday) | NOT STARTED
551 | 2026 |  | Fall Opening | RH Official Opening Date (Saturday) |  |  | 2026-08-23 (Sunday) | 2026-08-23 (Sunday) | NOT STARTED
552 | 2026 |  | Academic | Last Day to Sign Up for 4 month Payment Plan |  |  | 2026-08-24 (Monday) | 2026-08-24 (Monday) | NOT STARTED
553 | 2026 |  | Academic | Financial Aid Consortium Agreements Due |  |  | 2026-08-26 (Wednesday) | 2026-08-26 (Wednesday) | NOT STARTED
554 | 2026 |  | Academic | ND Resident Tuition Rate Applications Due |  |  | 2026-08-26 (Wednesday) | 2026-08-26 (Wednesday) | NOT STARTED
555 | 2026 |  | Housing Applications and Assignments | Fall RH No Shows Due |  |  | 2026-08-27 (Thursday) | 2026-08-27 (Thursday) | NOT STARTED
556 | 2026 |  | Academic | Fall First Full Day of Classes |  |  | 2026-08-27 (Thursday) | 2026-08-27 (Thursday) | NOT STARTED
557 | 2026 |  | Academic | UND Bookstore Charging Ends |  |  | 2026-08-30 (Sunday) | 2026-08-30 (Sunday) | NOT STARTED
558 | 2026 |  | Academic | Financial Aid Census Date |  |  | 2026-09-04 (Friday) | 2026-09-04 (Friday) | NOT STARTED
559 | 2026 |  | Academic | Fall Last Day to add or drop courses without record |  |  | 2026-09-04 (Friday) | 2026-09-04 (Friday) | NOT STARTED
560 | 2026 |  | Academic | Fall last day to submit an employee tuition waiver |  |  | 2026-09-04 (Friday) | 2026-09-04 (Friday) | NOT STARTED
561 | 2026 |  | Housing Applications and Assignments | RH Fall Room Change Begins |  |  | 2026-09-08 (Tuesday) | 2026-09-08 (Tuesday) | NOT STARTED
562 | 2026 |  | Academic | Fall Excess Financial Aid and Scholarship Student Refunds Begin |  |  | 2026-09-11 (Friday) | 2026-09-11 (Friday) | NOT STARTED
563 | 2026 |  | Academic | Fall Charges Due (No late fee until October 15) |  |  | 2026-09-11 (Friday) | 2026-09-11 (Friday) | NOT STARTED
564 | 2026 |  | Academic | Last Day to submit incomplete work from Spring and Summer |  |  | 2026-09-13 (Sunday) | 2026-09-13 (Sunday) | NOT STARTED
565 | 2026 |  | Campus Events | Homecoming |  |  | 2026-09-14 (Monday) | 2026-09-19 (Saturday) | NOT STARTED
566 | 2026 |  | Campus Events | Hawktoberfest |  |  | 2026-09-18 (Friday) | 2026-09-18 (Friday) | NOT STARTED
567 | 2026 |  | Academic | Fall Enrollment Census Date |  |  | 2026-09-23 (Wednesday) | 2026-09-23 (Wednesday) | NOT STARTED
568 | 2026 |  | Academic | Last day to sign up for 3 month payment plan |  |  | 2026-09-24 (Thursday) | 2026-09-24 (Thursday) | NOT STARTED
569 | 2026 |  | Academic | Last day for instructors to turn in "Removal of Incomplete" form to registrar |  |  | 2026-09-27 (Sunday) | 2026-09-27 (Sunday) | NOT STARTED
570 | 2026 |  | Housing Applications and Assignments | Fall Apartment Notice to Vacate Reminder |  |  | 2026-10-01 (Thursday) | 2026-10-01 (Thursday) | NOT STARTED
571 | 2026 |  | Academic | Fall Scholarship Central Applications open |  |  | 2026-10-01 (Thursday) | 2026-10-01 (Thursday) | NOT STARTED
572 | 2026 |  | Academic | Last day to withdraw to zero credits (regular session) for 75% refund |  |  | 2026-10-04 (Sunday) | 2026-10-04 (Sunday) | NOT STARTED
573 | 2026 |  | Campus Events | Family Weekend |  |  | 2026-10-09 (Friday) | 2026-10-11 (Sunday) | NOT STARTED
574 | 2026 |  | Academic | Last day to pay Fall charges to avoid late fee |  |  | 2026-10-15 (Thursday) | 2026-10-15 (Thursday) | NOT STARTED
575 | 2026 |  | Admissions and Orientation | MEA/NDEA Weekend |  |  | 2026-10-17 (Saturday) | 2026-10-18 (Sunday) | NOT STARTED
576 | 2026 |  | Academic | Spring Course registration date/time available in campus connection |  |  | 2026-10-25 (Sunday) | 2026-10-25 (Sunday) | NOT STARTED
577 | 2026 |  | Academic | Spring 2025 Course Registration Time/Date Available in Campus Connection |  |  | 2026-10-25 (Sunday) | 2026-10-25 (Sunday) | NOT STARTED
578 | 2026 |  | Academic | Spring Semester early registration begins |  |  | 2026-10-28 (Wednesday) | 2026-10-28 (Wednesday) | NOT STARTED
579 | 2026 |  | Fall Closing | Fall End of Semester Communication Starts |  |  | 2026-11-01 (Sunday) | 2026-11-01 (Sunday) | NOT STARTED
580 | 2026 |  | Campus Events | First Generation Student Celebration | Asst Director, Residential Experiences | Internal | 2026-11-02 (Monday) | 2026-11-06 (Friday) | NOT STARTED
581 | 2026 |  | Academic | Last day to withdraw to zero credits (regular session) for 50% refund |  |  | 2026-11-03 (Tuesday) | 2026-11-03 (Tuesday) | NOT STARTED
582 | 2026 |  | Housing Applications and Assignments | RH Fall Room Cancellations |  |  | 2026-11-09 (Monday) | 2026-11-09 (Monday) | NOT STARTED
583 | 2026 |  | Housing Applications and Assignments | RH Late Dept/Semester Break App |  |  | 2026-11-09 (Monday) | 2026-12-21 (Monday) | NOT STARTED
584 | 2026 |  | Academic | Fall Last day to change to or from S/U grading for regular session class |  |  | 2026-11-15 (Sunday) | 2026-11-15 (Sunday) | NOT STARTED
585 | 2026 |  | Academic | Fall Last Day to withdraw from term or drop with record |  |  | 2026-11-15 (Sunday) | 2026-11-15 (Sunday) | NOT STARTED
586 | 2026 |  | Campus Events | International Education Week | Asst Director, Residential Experiences | Internal | 2026-11-16 (Monday) | 2026-11-20 (Friday) | NOT STARTED
587 | 2026 |  | Housing Applications and Assignments | RH Spring Early Arrival Application |  |  | 2026-11-18 (Wednesday) | 2026-11-18 (Wednesday) | NOT STARTED
588 | 2026 |  | Academic | Thanksgiving Break |  |  | 2026-11-27 (Friday) | 2026-11-29 (Sunday) | NOT STARTED
589 | 2026 |  | Housing Applications and Assignments | RH Room Change - Fall to Spring |  |  | 2026-12-01 (Tuesday) | 2026-12-05 (Saturday) | NOT STARTED
590 | 2026 |  | Academic | Spring current student 5 month payment plan opens |  |  | 2026-12-01 (Tuesday) | 2026-12-01 (Tuesday) | NOT STARTED
591 | 2026 |  | Academic | Spring tuition and fee charges on campus connection |  |  | 2026-12-01 (Tuesday) | 2026-12-01 (Tuesday) | NOT STARTED
592 | 2026 |  | Academic | Fall Deadline for Undergraduates to Apply for Fall Graduation |  |  | 2026-12-06 (Sunday) | 2026-12-06 (Sunday) | NOT STARTED
593 | 2026 |  | Housing Applications and Assignments | RH Spring Room Assignments |  |  | 2026-12-08 (Tuesday) | 2026-12-10 (Thursday) | NOT STARTED
594 | 2026 |  | Theme Meal | Moonlight Breakfast (Wilkerson Commons only) -- Housing Program | Marketing/ARH |  | 2026-12-11 (Friday) | 1900-12-30 (Sunday) | NOT STARTED
595 | 2026 |  | Academic | Fall Last Day of Classes |  |  | 2026-12-12 (Saturday) | 2026-12-12 (Saturday) | NOT STARTED
596 | 2026 |  | Academic | Spring last day to submit family member tuition waivers |  |  | 2026-12-13 (Sunday) | 2026-12-13 (Sunday) | NOT STARTED
597 | 2026 |  | Academic | Fall Reading and Review Day |  |  | 2026-12-13 (Sunday) | 2026-12-13 (Sunday) | NOT STARTED
598 | 2026 |  | Academic | Fall Finals Week |  |  | 2026-12-16 (Wednesday) | 2026-12-20 (Sunday) | NOT STARTED
599 | 2026 |  | Fall Closing | Fall RH Close (Sunday) |  |  | 2026-12-20 (Sunday) | 2026-12-20 (Sunday) | NOT STARTED
600 | 2026 |  | Academic | Fall Commencement |  |  | 2026-12-20 (Sunday) | 2026-12-20 (Sunday) | NOT STARTED
601 | 2026 |  | Housing Applications and Assignments | RH End of Fall Term (Sunday) |  |  | 2026-12-21 (Monday) | 2026-12-21 (Monday) | NOT STARTED
602 | 2026 |  | Academic | Fall Grades Due |  |  | 2026-12-24 (Thursday) | 2026-12-24 (Thursday) | NOT STARTED
603 | 2026 |  | Academic | Spring last day to sing up for 5 month payment plan |  |  | 2026-12-24 (Thursday) | 2026-12-24 (Thursday) | NOT STARTED
604 | 2026 |  | Academic | Spring current student 4 month payment plan opens |  |  | 2026-12-25 (Friday) | 2026-12-25 (Friday) | NOT STARTED
605 | 2026 |  | Spring Opening | RH Spring Opening (Sunday) |  |  | 2027-01-11 (Monday) | 2027-01-11 (Monday) | NOT STARTED
606 | 2026 |  | Academic | Spring financial aid consortium agreements due |  |  | 2027-01-13 (Wednesday) | 2027-01-13 (Wednesday) | NOT STARTED
607 | 2026 |  | Academic | Spring ND Resident Tuition Rate applications due |  |  | 2027-01-13 (Wednesday) | 2027-01-13 (Wednesday) | NOT STARTED
608 | 2026 |  | Academic | Spring First Full Day of Classes |  |  | 2027-01-14 (Thursday) | 2027-01-14 (Thursday) | NOT STARTED
609 | 2026 |  | Housing Applications and Assignments | Spring RH No Shows Due |  |  | 2027-01-15 (Friday) | 2027-01-15 (Friday) | NOT STARTED
610 | 2026 |  | Academic | Spring last day to add/drop or withdraw (regular session for a 100% refund |  |  | 2027-01-23 (Saturday) | 2027-01-23 (Saturday) | NOT STARTED
611 | 2026 |  | Academic | Spring Financial Aid Census date |  |  | 2027-01-23 (Saturday) | 2027-01-23 (Saturday) | NOT STARTED
612 | 2026 |  | Academic | Spring last day to submit an employee tuition waiver |  |  | 2027-01-23 (Saturday) | 2027-01-23 (Saturday) | NOT STARTED
613 | 2026 |  | Academic | Spring Last day to sign up for 4 month payment plan |  |  | 2027-01-24 (Sunday) | 2027-01-24 (Sunday) | NOT STARTED
614 | 2026 |  | Academic | Spring Enrollment Census Date |  |  | 2027-01-24 (Sunday) | 2027-01-24 (Sunday) | NOT STARTED
615 | 2026 |  | Academic | Spring 3 month playment plan opens |  |  | 2027-01-25 (Monday) | 2027-01-25 (Monday) | NOT STARTED
616 | 2026 |  | Housing Applications and Assignments | RH Spring Room Change Opens |  |  | 2027-01-26 (Tuesday) | 2027-01-26 (Tuesday) | NOT STARTED
617 | 2026 |  | Academic | Spring excess finacial aid and scholarshiop student refunds begin |  |  | 2027-01-29 (Friday) | 2027-01-29 (Friday) | NOT STARTED
618 | 2026 |  | Academic | Spring Charges Due (No late fee until March 15) |  |  | 2027-01-29 (Friday) | 2027-01-29 (Friday) | NOT STARTED
619 | 2026 |  | Academic | Spring last day to sign up for 3 month payment plan |  |  | 2027-02-24 (Wednesday) | 2027-02-24 (Wednesday) | NOT STARTED
620 | 2026 |  | Housing Applications and Assignments | RH Summer Application |  |  | 2027-03-01 (Monday) | 2027-03-01 (Monday) | NOT STARTED
621 | 2026 |  | Academic | Spring last day to withdraw for 75% refund |  |  | 2027-03-07 (Sunday) | 2027-03-07 (Sunday) | NOT STARTED
622 | 2026 |  | Academic | Spring Break |  |  | 2027-03-10 (Wednesday) | 2027-03-14 (Sunday) | NOT STARTED
623 | 2026 |  | Academic | Spring last day to pay charges with no late fee |  |  | 2027-03-15 (Monday) | 2027-03-15 (Monday) | NOT STARTED
624 | 2026 |  | Academic | Spring last day to withdraw for a 50% refund |  |  | 2027-04-01 (Thursday) | 2027-04-01 (Thursday) | NOT STARTED
625 | 2026 |  | Housing Applications and Assignments | RH Spring Room Change Closes |  |  | 2027-04-03 (Saturday) | 2027-04-03 (Saturday) | NOT STARTED
626 | 2026 |  | Academic | Spring last day to change to/from SU grading |  |  | 2027-04-11 (Sunday) | 2027-04-11 (Sunday) | NOT STARTED
627 | 2026 |  | Academic | Spring Last Day to withdraw from term or drop with record |  |  | 2027-04-11 (Sunday) | 2027-04-11 (Sunday) | NOT STARTED
628 | 2026 |  | Housing Applications and Assignments | Spring Late Departure |  |  | 2027-04-14 (Wednesday) | 2027-04-14 (Wednesday) | NOT STARTED
629 | 2026 |  | Housing Applications and Assignments | RH Summer Room Assignments |  |  | 2027-04-14 (Wednesday) | 2027-04-14 (Wednesday) | NOT STARTED
630 | 2026 |  | Housing Applications and Assignments | Apartment Summer Assignment Rolls |  |  | 2027-04-15 (Thursday) | 2027-04-15 (Thursday) | NOT STARTED
631 | 2026 |  | Spring Closing | RollOff Dumpsters for RHs and Apartments |  |  | 2027-04-15 (Thursday) | 2027-04-15 (Thursday) | NOT STARTED
632 | 2026 |  | Spring Closing | Bicycle Apandoned Property Process |  |  | 2027-04-15 (Thursday) | 2027-04-15 (Thursday) | NOT STARTED
633 | 2026 |  | Academic | Easter Break |  |  | 2027-04-18 (Sunday) | 2027-04-21 (Wednesday) | NOT STARTED
634 | 2026 |  | Theme Meal | Moonlight Pizza -- Housing Program | Marketing/ARH |  | 2027-05-07 (Friday) | 2027-05-07 (Friday) | NOT STARTED
635 | 2026 |  | Academic | Spring last day of classes |  |  | 2027-05-08 (Saturday) | 2027-05-08 (Saturday) | NOT STARTED
636 | 2026 |  | Academic | Spring Reading and Review Day |  |  | 2027-05-09 (Sunday) | 2027-05-09 (Sunday) | NOT STARTED
637 | 2026 |  | Academic | Spring Finals Week |  |  | 2027-05-12 (Wednesday) | 2027-05-16 (Sunday) | NOT STARTED
638 | 2026 |  | Spring Closing | Spring RH Close (Saturday) |  |  | 2027-05-16 (Sunday) | 2027-05-16 (Sunday) | NOT STARTED
639 | 2026 |  | Summer Opening | RH Summer Halls Open |  |  | 2027-05-17 (Monday) | 2027-05-17 (Monday) | NOT STARTED
640 | 2026 |  | Academic | Spring Commencement |  |  | 2027-05-17 (Monday) | 2027-05-17 (Monday) | NOT STARTED
641 | 2026 |  | Academic | Summer First Day of Classes |  |  | 2027-05-19 (Wednesday) | 2027-05-19 (Wednesday) | NOT STARTED
642 | 2026 |  | Academic | Spring Grades Due |  |  | 2027-05-21 (Friday) | 2027-05-21 (Friday) | NOT STARTED
643 | 2026 |  | Summer Closing | RH Summer Hall Closes (Sunday) |  |  | 2027-08-04 (Wednesday) | 2027-08-04 (Wednesday) | NOT STARTED
644 | 2026 | Fall | Academic | Test1A | Test1 | External | 2025-09-18 (Thursday) | 2025-09-18 (Thursday) | IN PROGRESS

## Changelog
Timestamp | Action | Task ID | Field Changed | Old Value | New Value
2025-09-18 07:48:50 | ADD | 644 | ENTIRE TASK |  | Test1
2025-09-18 07:50:35 | EDIT | 432 | Fiscal Year | 2026 | 2026
2025-09-18 07:50:35 | EDIT | 432 | SEMESTER |  | nan
2025-09-18 07:50:35 | EDIT | 432 | PROGRESS | NOT STARTED | IN PROGRESS